## TestCase
Product Name |  | Facebook | TC Start Date | 2023-09-01 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Login | TC End Date | 2023-09-01 | TC Execution End Date | - - |  |  |  |  | PASS | 14
Epic |  |  | Test Case Developed By | Jahanara | Browser (tested) | Yes |  |  |  |  | FAIL | 1
Developer Name (TL) |  |  | Test Case Reviewed By | [7 empty] | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 15
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Login | Browser Compatibility Testing | Login | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2.Then go https://www.facebook.com/ |  |  | Passed
2 |  | UI/UX | Login | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing. | Should be clicked on the "Login" link. | Found as per expectation. | None | 1.Go (https://www.facebook.com) in Google Chrome. 2.Check the alignment of elements (input fields, buttons, links). 3.Repeat steps 1 and 2 in Firefox, Safari, and Microsoft Edge. 4.Compare element alignment across browsers. |  |  | Passed
3 |  |  |  | Verify all login-related elements and fields are present on the login page. | All elements should be present, functional, and visually appealing | Found as per expectation. | None | 1.Go to https://www.facebook.com. 2.Locate the login section on the right-hand side of the page. 3.Verify the presence of the following elements:Email/Phone input field,Password input field,Login button,Links such as "Forgot Password?" and "Create New Account" |  |  | Passed
4 |  |  |  | Verify the displayed element are in alignment from. | Elements should be in aligment from. . | Found as per expectation. | None | 1.Open the Facebook login page on various browsers (Chrome, Firefox, Safari, etc.). 2.Check if the input fields, buttons, and links are aligned as expected. 3.Ensure that the layout is consistent across different devices and screen sizes. |  |  | Passed
5 |  |  |  | Verify that the size, color, and UI of different elements should match the specifications. | Should be as per the client requirement | Found as per expectation. | None | 1.Open the Facebook login page on a browser. 2.Inspect the size of key UI elements like the login button, input fields, and links. 3.Verify that the color of elements matches the design specifications. 4.Check that the UI style (e.g., font, button shape, borders) aligns with the design specifications. |  |  | Passed
6 |  |  |  | Verify that the login page of the application is responsive and aligns properly on different screen resolutions and devices | The login page layout should adapt and resize properly on different screen resolutions | Found as per expectation. | None | 1.Open Facebook login page (https://www.facebook.com) on a desktop browser. 2.Resize the browser to different resolutions: 1920x1080, 1366x768, 768x1280, 375x667. 3.Check if the elements (input fields, buttons) align properly and are responsive. 4.Open the login page on a mobile device and check in both portrait and landscape modes. 5.Verify across different browsers (Chrome, Firefox, Safari, Edge). |  |  | Passed
7 |  |  |  | Hover and Focus States for Facebook Login Elements | All interactive elements (Login button, input fields, Forgot Password, Create New Account links) should have clear hover and focus states. | Found as per expectation. | None | 1.Open https://www.facebook.com in a browser. 2.Hover over the Login button. 3.Click or tab to the Email/Phone input field. 4.Click or tab to the Password input field. 5.Hover over the Forgot Password? link. 6.Hover over the Create New Account link. |  |  | Passed
8 |  | Funtional testing |  | Verify Login with Empty Fields | A message should be displayed indicating that both fields are required (e.g., "Please enter both your email/phone and password | Found as per expectation. | None | 1.Open the Facebook login page. 2.Leave the email/phone number and/or password fields empty. 3.Click the Login button. |  |  | Passed
10 |  |  |  | Verify Login with Invalid Credentials | The user should see an error message like "The email or phone number you’ve entered doesn’t match any account | Found as per expectation. | jaha@gmail.com,0148555,RS | 1.Open the Facebook login page. 2.Enter an invalid email -jaha@,phone number-0148555 and password-RS. Click the Login button. |  |  | Passed
11 |  |  |  | Verify “Forgotten Password” Link | The user should be redirected to the password recovery page | Found as per expectation. | None | 1.Open the Facebook login page. 2.Click the Forgotten password? link. |  |  | Passed
12 |  |  |  | Verify “Create New Account” Link | The user should be redirected to the Facebook sign-up page. | Found as per expectation. | None | 1.Open the Facebook login page. 2.Click the Create New Account button. |  |  | Passed
13 |  |  |  | Verify Password Visibility Toggle | The password should toggle between masked and visible | Found as per requirment | password123 | 1.Open the Facebook login page. 2.Enter password123 in the Password field. 3.Click the eye icon to toggle password visibility. |  |  | Passed
14 |  |  |  | Verify that the password entered should be in encrypted form. | The password entered should be in encrypted form. | Found as per expectation. | password123 | 1.Open the Facebook login page (https://www.facebook.com). 2.Locate the Password input field. 3.Enter any password just like password123in the field. Observe how the characters appear as you type. |  |  | Passed
15 |  |  |  | Verify Login with Valid Credentials | The user should be logged in successfully and redirected to the Facebook home page | Found as per expectation but its goes two factor verifacation page . | jaha@gmail.com,0148555RS@@sr | 1.Open the Facebook login page. 2.Enter jaha@gmail.com in email feild and 0148555RS@@sr in password field 3.Click the Login button. | https://drive.google.com/file/d/1wOqXzR3fWEH2zxPq1SgeNbSxopdub7Ee/view?usp=sharing |  | Failed
16 |  |  |  | Verify Login for User with Two-Factor Authentication | The user should be successfully logged in after entering the correct authentication code. | Found as per expectation. | jaha@gmail.com,0148555RS@@sr,666888 | 1.Open the Facebook login page. 2.Enter jaha@gmail.com in email feild and 0148555RS@@sr in password field 3.Enter the code sent for two-factor authentication (if enabled). |  |  | Passed

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Facebook
Module Name | Login |  |  |  |  | Total No. | Status
Feature Name
Test Case Version | 1 |  |  |  |  | 14 | PASS
Written By | Suchi |  |  |  |  | 1 | FAIL
Executed By | Suchi |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Suchi |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 14 | 1 | 0 | 0 | 15
Grand Total | 14 | 1 | 0 | 0 | 15
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.